## Tasks_Template
Task_Number | Task_Name | Duration_Days | Predecessor_Task_Number
1 | H/W Order Completed | 0
2 | IRM Ordering Completed | 0
3 | Cabaling Service PO Available | 0
4 | Application service PO Availibility | 0
5 | Scope defined and available | 0
6 | Facility Readiness and allocation | 0
7 | Rack Layout availibility | 0
8 | Cable length to be available | 0
9 | Project Initiation | 1
10 | H/W at NWH | 2 | 9
11 | IRM at NWH | 2 | 9
12 | NSIP ID Creation | 1 | 10
13 | DMTO/SO1 Creation for HW | 1 | 12
14 | HW @SWH | 5 | 13
15 | HW @Site | 2 | 14
16 | IRM disptatched | 1 | 11
17 | IRM @SWH | 5 | 16
18 | IRM @Site | 2 | 17
19 | HW Rack-stack & Power ON | 2 | 15
20 | P2P Availibility | 3 | 9
21 | Final P2P Upload | 1 | 20
22 | P2P Approved | 2 | 21
23 | ToR Site Survey | 1 | 22
24 | TOR HW I & C | 2 | 23
25 | IP readiness | 4 | 24
26 | Ilo Reachability check | 1 | 25
27 | Server to ToR Cabaling | 2 | 26
28 | Lebeling | 1 | 27
29 | HW HOTO Checklist Imp. | 2 | 27
30 | SO2 Completion | 1 | 29
31 | HW Handover to Application Team | 1 | 29
32 | OS Installation | 3 | 31
33 | Application I & C | 4 | 32
34 | SO3 Submission | 1 | 33
35 | SO4 Completion | 1 | 34
36 | NEID Availibility | 4 | 35
37 | Nw Integration | 5 | 33
38 | OSS Integration | 5 | 36
39 | Security Clearance | 3 | 37
40 | NIT Clearance | 2 | 37
41 | Testing Offered | 1 | 40
42 | Testing Completion | 5 | 41
43 | ATP Offer | 1 | 42
44 | ATP Acceptance | 2 | 43
45 | IDC - Node Offer | 1 | 42
46 | IDC - Node Acceptance | 5 | 45
47 | NOC - Node offer | 1 | 43
48 | NOC - Node Acceptance | 1 | 47
49 | Ready for Service | 1 | 48
50 | Go Live | 2 | 49